## W7-10
Task Name | Date (mm/dd/yyyy) | Time Worked | Resources | Outcomes | To Do
Start EC2 Sever | 03/05/2021 | 30 mins | https://www.youtube.com/watch?v=IIBy6d2whEg | Connected to the EC2 via the remote desktop and started my own ArcGIS Server hosted on an EC2 in AWS. | Publish the Canada map service from Week 6 to my personal AWS EC2 running ArcGIS Server.
Publish Canada map service to EC2 Server | 03/05/2021 | 30 mins | 1. https://enterprise.arcgis.com/en/server/latest/manage-data/windows/registering-your-data-with-arcgis-server-using-manager.htm 2. https://www.youtube.com/watch?v=nIRlZN9ECwY | 1. Copied "Canada" shapefile from my local computer to the EC2 root directory (C:\GISWorkspace\Canada) 2. Created an ArcGIS Pro project (on local computer) with the Canada shapefile 3. Add new server to ArcGIS Pro project: https://kluangkh.duckdns.org:6443/arcgis 3. Published Canada map service to EC2 ArcGIS server via registering the shapefile data: https://kluangkh.duckdns.org/arcgis/rest/services/Canada/MapServer | Create my own DuckDNS and obtain an SSL certificate using Win Acme.
Create DuckDNS and obtain an SSL certificate | 03/05/2021 | 15 mins | https://www.youtube.com/watch?v=V2o07DMyNkc&t=23s | Duck DNS domain (secure, valid certificate): https://kluangkh.duckdns.org/ | Read about ArcGIS Services
Read about ArcGIS Services | 03/05/2021 | 20 mins | 1. https://enterprise.arcgis.com/en/server/latest/publish-services/windows/services-in-arcgis-enterprise.htm 2. https://enterprise.arcgis.com/en/server/latest/publish-services/windows/relationships-between-web-services-and-portal-items.htm | Read both articles to gain a better understanding of ArcGIS services.
Watch video about Managing Portal from ArcGIS Pro | 03/05/2021 | 20 mins | https://www.youtube.com/watch?v=KItDcnDQce0 | Watched the entire video
Create a personal AWS account and deploy the ArcGIS server | 03/10/2021 | 60 mins | AWS EC2 Setup Instructions (PDF) | Personal AWS account created, AMI from Shawn put on my EC2 console, ArcGIS Server deployed and running | Create my own DuckDNS and obtain an SSL certificate using Win Acme.
Create DuckDNS and obtain an SSL certificate | 03/10/2021 | 15 mins | https://www.youtube.com/watch?v=V2o07DMyNkc&t=23s | Duck DNS domain (secure, valid certificate): https://kluangkh99.duckdns.org/ | Publish the Canada map service from Week 6 to this AWS EC2 running ArcGIS Server.
Publish Canada map service to EC2 Server | 03/10/2021 | 30 mins | 1. https://enterprise.arcgis.com/en/server/latest/manage-data/windows/registering-your-data-with-arcgis-server-using-manager.htm 2. https://www.youtube.com/watch?v=nIRlZN9ECwY | 1. Copied "Canada" shapefile from my local computer to the EC2 root directory (C:\GISWorkspace\Canada) 2. Created an ArcGIS Pro project (on local computer) with the Canada shapefile 3. Add new server to ArcGIS Pro project: https://kluangkh99.duckdns.org:6443/arcgis 3. Published Canada map service to EC2 ArcGIS server via registering the shapefile data: https://kluangkh99.duckdns.org/arcgis/rest/services/Canada/MapServer
Meet with client to discuss web component of the project. | 03/16/2021 | 60 mins | https://projects.geocommunity.net/projectviewer.html?id=2110 | Client asks for a dynamic web map of headwater streams in the Rick Lake Plains area. Esri technology is available to the organization. | Decide (as a group) which web configurable solution would be suitable for the project.
Formulate a Problem Statement with project group members. | 03/18/2021 | 30 mins | https://ssfcollege-my.sharepoint.com/:x:/g/personal/shawnm_flemingcollege_ca/EZG_N-Cj279PpbMj3y_8aywBHwomszLWT4PO7lwzGy8Xkw?e=NszAnp | Version 1.0 of the problem statement completed with the ideal, reality, consequences, proposal and technology used filled out. ArcGIS Experience Builder will be used for the web application (configurable solution). | Review problem statement with Shawn.
Meet with Shawn to review problem statement. | 03/19/2021 | 30 mins | 1. https://ssfcollege-my.sharepoint.com/:x:/g/personal/shawnm_flemingcollege_ca/EZG_N-Cj279PpbMj3y_8aywBHwomszLWT4PO7lwzGy8Xkw?e=NszAnp 2. https://doc.arcgis.com/en/experience-builder/gallery/ | Version 1.0 of the problem statement revised; scope was changed to be more manageable for project duration. | Review configurable web solutions (week 9 checklist).
Review of Esri Configurables (ArcGIS Enterprise Builder, WebApps, ArcGIS Dashboard, ArcGIS StoryMaps, Configurable Apps) | 03/19/2021 | 45 mins | 1. https://www.esri.com/en-us/arcgis/products/arcgis-experience-builder/overview 2. https://www.esri.com/en-us/arcgis/products/arcgis-web-appbuilder/overview 3. https://www.esri.com/en-us/arcgis/products/arcgis-dashboards/resources 4. https://storymaps.arcgis.com/ 5. https://github.com/topics/4x-configurable-app | Briefly read through each Esri Configurable to get a basic understanding of its capabilities and use cases. | Read about Open Source solutions.
Review of Open Source configurable solutions (Leaflet, Geoserver, OSM, qField, KoboToolbox) | 03/19/2021 | 45 mins | 1. Leaflet: https://leafletjs.com/index.html 2. Geoserver: https://youtu.be/7bbq3gWEXI8, https://youtu.be/Gjfb4cF_j8k, https://youtu.be/ym1b2NDDAQY, https://youtu.be/8lhwczAjCec 3. OSM: https://www.openstreetmap.org/#map=3/71.34/-96.82 4. qField: https://qfield.org/ 5. KoboToolbox: https://www.kobotoolbox.org/ | Briefly read through each Open Source configurable solution to get a basic understanding of its capabilities and use cases. Watched videos about GeoServer. | Review Vertigis Geocortex and Rolta's OnPoint.
Review of Geocortex and Rolta OnPoint. | 03/20/2021 | 60 mins | 1. https://www.youtube.com/watch?v=olp1q9bRuoU 2. http://www.youtube.com/watch?v=0iDtvIEiw7k 3. http://www.youtube.com/watch?v=fGZqyeyh__o 4. http://www.youtube.com/watch?v=vNyfOtRukcs | Watched demonstration videos about GeoCortex, looked at demo sites using Geocortex Essentials 4 and Geocortex 5, looked at one example of OnPoint. | Create a Geocortex site.
Create my own Geocortex site on the Luna server | 03/20/2021 | 30 mins | Geocortex Intro (PDF) | Geocortex Site REST Endpoint: https://luna.flemingcollege.ca/Geocortex/Essentials/REST/sites/Kristine_Luangkhot Viewer REST Endpoint: https://luna.flemingcollege.ca/Geocortex/Essentials/REST/sites/Kristine_Luangkhot/viewers Geocortex Site in Viewer: https://luna.flemingcollege.ca/Html5Viewer/Index.html?configBase=https://luna.flemingcollege.ca/Geocortex/Essentials/REST/sites/Kristine_Luangkhot/viewers/HTML5KristineLuangkhot/virtualdirectory/Resources/Config/Default | Review Mapbox API.
Create a Mapbox account and get an access token | 03/21/2021 | 15 mins | https://account.mapbox.com/auth/signup/ | Mapbox account with username 'ksluangkhot' created and public access token created: pk.eyJ1Ijoia3NsdWFuZ2tob3QiLCJhIjoiY2ttamZmaXU1MG01ejJvbno1YWR5ZXZiMyJ9.Gw8oy40EAUoi2o1s7fqSQQ | Create my own style using Mapbox Studio.
Create my own Mapbox style | 03/21/2021 | 30 mins | https://docs.mapbox.com/studio-manual/reference/styles/ | Used Mapbox Studio to create my own style called "Streets": https://api.mapbox.com/styles/v1/ksluangkhot/ckmjfk1gw0rzy18js7ahmo4l5.html?fresh=true&title=view&access_token=pk.eyJ1Ijoia3NsdWFuZ2tob3QiLCJhIjoiY2ttamZmaXU1MG01ejJvbno1YWR5ZXZiMyJ9.Gw8oy40EAUoi2o1s7fqSQQ | Modify Mapbox demos using my ArcGIS Server map service.
Modify two Mapbox demos using my AWS EC2 ArcGIS Server Canada map service. | 03/21/2021 | 60 mins | 1. https://shawnmflemingc.github.io/mapboxdemo.html 2. https://shawnmflemingc.github.io/mapboxgeojson.html 3. https://kluangkh99.duckdns.org/arcgis/rest/services/Canada/MapServer | Two Mapbox demos published and hosted on my GitHub repository. 1. Map Service: https://kluangkhflemingc.github.io/geom99/mapbox.html 2. GeoJson Return: https://kluangkhflemingc.github.io/geom99/mapboxgeojson.html
Advisor meeting with Paige Wearing - updates on the web project | 03/23/2021 | 50 mins | N/A | Told Paige about our plan to use ArcGIS Experience Builder to prototype a solution for the project. No concerns thus far.

## W10-11
Task Name | Date (mm/dd/yyyy) | Time Worked | Resources | Outcomes | To Do
Clip and upload data to be used in ArcGIS Experience Builder/AGOL | 03/25/2021 | 30 mins | ArcGIS Pro -> Geoprocessing Tool -> Clip | Watercourses and waterbodies available on Ontario GeoHub clipped to the study area (Rick Lake Plains Natural Area) in ArcGIS Pro, file geodatabase with all data sent to team members. | Team member leading web development will upload data to AGOL and create a draft application in ArcGIS Experience Builder. Meet with Shawn to update him on the team's progress.
Meet with Shawn to provide an update on the project | 03/26/2021 | 15 mins | ArcGIS Experience Builder (draft): https://experience.arcgis.com/experience/faa94141a36048dcbcb9bac5b83db5b0/ | Explained the struggles we were having with ArcGIS Experience Builder (bugs, navigation, etc.). Decided that we will work with Experience Builder for another week and start an ArcGIS StoryMap as a back-up solution. | Continue working on our Experience Builder draft, start a StoryMap, and create a webpage to document the project lifecycle.
Create a GitHub repository and webpage to document the project workflow | 03/26/2021 | 90 mins | GitHub (create new repository), Visual Studio Code (add HTML pages, CSS stylesheet and JS script) | 1. GitHub repository (all team members listed as contributors): https://github.com/kluangkhflemingc/nccweb 2. Project webpage: https://kluangkhflemingc.github.io/nccweb/ | Fill out the webpage with all the relevant information. Find more online resources related to ArcGIS Experience Builder.
Watch YouTube videos about ArcGIS Experience Builder | 03/27/2021 | 90 mins | 1. Get to Know ArcGIS Experience Builder: Build an Experience from Scratch (Esri Canada): https://www.youtube.com/watch?v=zQMBhtQOwwY 2. ArcGIS Experience Builder (Esri Events): https://www.youtube.com/watch?v=pNrsd5naN7U 3. Developing with ArcGIS Experience Builder (ArcGIS): https://www.youtube.com/watch?v=Vu6_pBa7zis&t=8s | Watched all three videos - got a better understanding of ArcGIS Experience Builder and made notes of the features/functionality that I liked. | Read the ArcGIS Developers' documentation about Experience Builder.
Read the ArcGIS Developers' documentation about Experience Builder. | 03/29/2021 | 30 mins | https://developers.arcgis.com/experience-builder/guide/core-concepts/ | Learned about adding and managing data, creating cutom widgets and creating custom themes using the Jimu JavaScript library in Experience Builder.
Advisor meeting with Paige Wearing - update on the web project. | 03/30/2021 | 15 mins | N/A | Asked Paige about what kind of questions we should ask the client when developing the web application - she said to ask about the support they have, whether they need a user manual alongside the application and whether they plan to do maitenance in the future. | Meet with client to further discuss the content and functionality they want from the web application.

## W11-12
Task Name | Date (mm/dd/yyyy) | Time Worked | Resources | Outcomes | To Do
Install ArcGIS Experience Builder (Developer Edition) onto my computer - use personal ArcGIS Developers account to install | 03/31/2021 | 30 mins | 1. https://www.youtube.com/watch?v=BcJxNaKuTxg 2. https://developers.arcgis.com/experience-builder/guide/install-guide/ (Server install option: Create Client ID on ArcGIS Developers site) | 1. Node.js 12+.x and ArcGIS Experience Builder Developer Edition downloaded and running on my computer 2. Client ID created on ArcGIS Developers site 3. server and client services installed and run 4. Screenshot of ArcGIS Experience Builder Developer Edition: https://raw.githubusercontent.com/kluangkhflemingc/nccweb/main/images/expbuild.png | Complete basic tutorials available on the ArcGIS Developers site to familiarize myself with ArcGIS Experience Builder Developer Edition.
Create a starter widget tutorial (ArcGIS Developers site) | 03/31/2021 | 15 mins | https://developers.arcgis.com/experience-builder/guide/create-a-starter-widget/ | 1. Base implementation for a widget created in my local file directory 2. Widget tested in ArcGIS Experience Builder by adding it to a new experience: https://raw.githubusercontent.com/kluangkhflemingc/nccweb/main/images/widget.JPG | 1. Get map coordinates tutorial 2. Add layers to a map tutorial
Meet with other groups using ArcGIS Experience Builder to give each other tips | 03/31/2021 | 45 mins | Adobe Connect | Each group shared a draft of their application and we talked about the features we liked and disliked. Figured out that we could share one draft of an experience in an AGOL group and give group members edit permissions. | 1. Get map coordinates tutorial 2. Add layers to a map tutorial
Group meeting to debrief meeting with other groups and discuss next steps. | 04/01/2021 | 30 mins | Microsoft Teams, ArcGIS Experience Builder (working draft) | Decided that each group member was going to make their own Experience Builder template/draft. Two group members will use Experience Builder while one will use Experience Builder Developer's Edition to compare workflows. | 1. Get map coordinates tutorial 2. Add layers to a map tutorial 3. Start a draft of the group web solution on Experience Builder Developer Edition
Get maps coordinates tutorial | 04/01/2021 | 30 mins | https://developers.arcgis.com/experience-builder/guide/get-map-coordinates/ | 1. Custom widget that displays latitude and longitude of the map created in my local file directory 2. Widget tested in ArcGIS Experience Builder by adding it to an experience: | 1. Add layers to a map tutorial 2. Start a draft of the group web solution on Experience Builder Developer Edition
Add layers to a map tutorial | 04/01/2021 | 30 mins | https://developers.arcgis.com/experience-builder/guide/add-layers-to-a-map/ | 1. Custom widget with a button to add a feature layer to the map created in my local file directory 2. Widget testing in ArcGIS Experience Builder by adding it to a new experience: | Use ArcGIS Experience Builder Developer Edition to create a draft of the group's web solution - data must first be uploaded to AGOL.
Upload data to my personal ArcGIS Online organization | 04/01/2021 | 15 mins | ArcGIS Pro, ArcGIS Online (https://ksaapuqbu7tupomc.maps.arcgis.com/home/index.html) | Study area polygon, clipped waterbodies and clipped watercourses uploaded from ArcGIS Pro to AGOL as hosted feature layers. | Use data to create a web map then add web map to a new experience in ArcGIS Experience Builder Developer Edition.
Create a web map to be used in Experience Builder. | 04/02/2021 | 30 mins | ArcGIS Map Viewer (Beta) | Web Map of the study area polygon, clipped waterbodies and clipped watercourses with the "Hybrid Imgaery" base map: https://ksaapuqbu7tupomc.maps.arcgis.com/home/webmap/viewer.html?webmap=3e6d9a125edc4a98b281930e0dee5b72 | Create a draft of the group's web solution in Experience Builder Developer Edition
Create a draft of the group's web solution in Experience Builder Developer Edition | 04/06/2021 | 60 mins | ArcGIS Experience Builder Developer Edition | Draft Experience using a template (will only load if server and client are started): https://localhost:3001/experience/2/ | Experiment with building custom widgets for the working draft.
Esri Developer Summit: attend the "ArcGIS Experience Builder: An Introduction" session | 04/06/2021 | 60 mins | https://dev2021.esri.com/live-stream/19764729/ArcGIS-Experience-Builder-An-Introduction | Attended the session and noted the widgets and workflows that I liked. Got some tips about navigation and sharing experiences. | Experiment with building custom widgets for the working draft.
Advisor meeting with Paige Wearing - update on the web project. | 04/06/2021 | 15 mins | N/A | Showed Paige the group's working draft in ArcGIS Experience Builder. No concerns thus far.

## W12-13
Task Name | Date (mm/dd/yyyy) | Time Worked | Resources | Outcomes | To Do
Meet with the client to further discuss what functionality they would like with the web solution. | 04/07/2021 | 45 mins | Microsoft Teams, ArcGIS Experience Builder (draft): https://experience.arcgis.com/experience/faa94141a36048dcbcb9bac5b83db5b0 | Client likes the idea of having filters to show different stream orders, symbolizing based on stream order and proposed the idea of showing connectivity when you click on a certain stream. | See if we show stream connectivity with our draft experience.
ArcGIS Experience Builder: Building Your First Widget (Demo) | 04/08/2021 | 30 mins | https://dev2021.esri.com/live-stream/19764740/ArcGIS-Experience-Builder-Building-Your-First-Widget | Watched the whole demo to create a custom widget that updates a list based on the filter selected for a feature layer. | Meet with team to discuss whether we want to continue with the Developer Edition.
Team meeting to discuss the templates each one of us created and plans for the application moving forward. | 04/08/2021 | 30 mins | Microsoft Teams, ArcGIS Experience Builder (drafts): 1) https://experience.arcgis.com/experience/faa94141a36048dcbcb9bac5b83db5b0 2) https://localhost:3001/experience/2/ | Discussed aspects from each template we all liked, decided that our final application will be configured in ArcGIS Experience Builder and should contain a home page that outlines the project and a page for the standalone web application. | Move the draft experience I created from Developer Edition to ArcGIS Experience Builder (online, Fleming organization).
Move the draft experience I created from Developer Edition to ArcGIS Experience Builder (online, Fleming organization). | 04/08/2021 | 3h 30mins | ArcGIS Experince Builder Developer Edition (draft): https://localhost:3001/experience/2/ | Brought everything in the draft over from ArcGIS Experience Builder Developer Edition to ArcGIS Experience Builder (in Fleming organization). Added more content to the template and embedded team member's draft application into the experience. https://experience.arcgis.com/experience/2d4f5b6920f94445a293a6102817eaac | Continue working on the draft as a team.
Meet with Shawn - review progress and receive recommendations for next steps. | 04/09/2021 | 15 mins | Adobe Connect, ArcGIS Experience Builder (drafts): 1) https://experience.arcgis.com/experience/2d4f5b6920f94445a293a6102817eaac 2) https://experience.arcgis.com/experience/faa94141a36048dcbcb9bac5b83db5b0 | Shawn liked the work we have done in Experience Builder thus far, but advised that we do not have to host everything in Experience Builder. Recommended that we try building something in ArcGIS Hub for the front-facing "webpage" solution. | Start a project in ArcGIS Hub to experiment with its functionality. Keep working on the Experience Builder draft and filling out our GitHub webpage (to be handed in and shown to future classes).
Fill the GitHub webpage documentating the work completed thus far. | 04/10/2021 | 60 mins | https://kluangkhflemingc.github.io/nccweb/ | Looked at examples from previous classes and filled our GitHub webpage with similar content (Project Background, Problem Statement, Team Members, Workflow). | Start a project in ArcGIS Hub, fill the Experience Builder draft with all the content we want and add more to the GitHub webpage.
Start a hub site application in ArcGIS Hub | 04/13/2021 | 30 mins | ArcGIS Hub | Created a hub site application and did an overview of the different components in a site https://happypuppies-fleming.hub.arcgis.com/ | Continue customizing the hub site application, complete the Experience Builder draft and complete the GitHub webpage.
Advisor meeting with Paige Wearing - update on the web project. | 04/13/2021 | 15 mins | Microsoft Teams | Debriefed Paige on the previous client meeting. No concerns thus far.

## W13-14
Task Name | Date (mm/dd/yyyy) | Time Worked | Resources | Outcomes | To Do
Team meeting to discuss our experience with ArcGIS Hub and plans for the application moving forward. | 04/15/2021 | 2h | Microsoft Teams ArcGIS Hub Site: https://rice-lake-plains-hydrology-fleming.hub.arcgis.com/ ArcGIS Experience Builder Draft: https://experience.arcgis.com/experience/2d4f5b6920f94445a293a6102817eaac GitHub Website: https://kluangkhflemingc.github.io/nccweb | Decided that we will continue working on the front-end webpage looking solution in ArcGIS Hub (Kathryn willl work on formatting the Hub Site), James will create two new web experiences to embed in the Hub Site and I will work on the GitHub website documenting the project (Final HTML Presentation). | Format the GitHub website so there's a cohesive layout/design and create sections that document our experience with each Esri configurable.
Meet with Shawn - review Hub Site and discuss next steps. | 04/16/2021 | 15 mins | Adobe Connect ArcGIS Hub Site: https://rice-lake-plains-hydrology-fleming.hub.arcgis.com/ | Shawn liked the content in our Hub Site, recommended that we continue refining the layout and gave us advice on how to show stream connectivity with the web experiences embedded in the site. Also discussed the GitHub webpage which Shawn would like handed in for Beta Delivery. | Prepare the GitHub website for Beta Delivery to Shawn.
Prepare the GitHub website for Beta Delivery - format images, write-up our experience with Esri configurable solutions and list project milestones. | 04/16/2021 | 2h 30 mins | Adobe Connect (team members on a call working on the GitHub repository simultaenously to ensure changes are pulled and pushed properly) GitHub Website: https://kluangkhflemingc.github.io/nccweb | All outcomes (linked markdown document): https://github.com/kluangkhflemingc/geom99/blob/main/log/April162021.md | Fill out the Timeline page and prepare the GitHub website for final submission.
Prepare the GitHub website for Final Submission - add a button at the bottom of the ArcGIS Solutions page so users can view the Hub Site in a new tab. | 04/17/2021 | 1h | GitHub Website (ArcGIS Solutions page): https://kluangkhflemingc.github.io/nccweb/solutions.html How to center a button: https://www.w3schools.com/howto/howto_css_center_button.asp Create a button that opens a HTML link in a new page: https://stackoverflow.com/questions/2906582/how-to-create-an-html-button-that-acts-like-a-link | Button placed under the 'Conclusions' section that opens the Hub Site in a new tab when clicked: https://kluangkhflemingc.github.io/nccweb/solutions.html. | Fill out the Timeline page and continue preparing the GitHub website for final submission.
Prepare GitHub website for Final Submission - add subheadings to the Timeline page according to project rubric. | 04/20/2021 | 30 mins | GitHub Website (Timeline page): https://kluangkhflemingc.github.io/nccweb/timeline.html | Subheadings such as 'Challenges Encountered', 'Learning Outcomes', 'Next Steps' and 'Future Improvements' added to each Milestone section of the Timeline page. | Fill out all sections and subheadings on the Timeline page and finalize GitHub website for final submission.
Prepare GitHub website for Final Submission - check if Beta Delivery has any CSS/HTML/JS errors and fix them. | 04/20/2021 | 45 mins | HTML Validator: https://validator.w3.org/ CSS Validator: https://jigsaw.w3.org/css-validator/ | All outcomes (linked markdown document with images): https://github.com/kluangkhflemingc/geom99/blob/main/log/April192021.md | Fill out the Timeline page and finalize the GitHub website for final submission.
Advisor meeting with Paige Wearing - update on the web project. | 04/20/2021 | 15 mins | Microsoft Teams | Debrief of the progress on the web project and how it can contribute to the collaboration project moving forward. No concerns thus far.